Game Plan: Equipment Snapshot and Project Cleanup (867)

Expedited course of action, revision 3  |  Prepared for John Feldhausen  |  October 14, 2026

# 1. Bottom Line

There are two separate tools with two separate jobs. Tool 1, the Snapshot, reads the 867 equipment master and everything it references, wherever those files live, and writes one new flattened DWG for the piping and electrical sets. It changes nothing it reads. Tool 2, the Project Cleanup, brings in the blocks the master borrows from other projects, explodes them, and writes them out (wblock) to a library folder inside 867, so the project stands on its own. Tool 1 is built and needs testing; Tool 2 is built next on the same foundation. Target: a measured snapshot within about three working days, and a cleaned 867 master by the end of week two.

# 2. The Two Tools

|  | Tool 1: Snapshot | Tool 2: Project Cleanup |
| --- | --- | --- |
| Job | Flatten everything into one 2D reference file | Make 867 self-contained: borrowed blocks become 867 library files |
| Reads | The master and all references, in any project | The master and the outside blocks it borrows |
| Writes | One new file (fixed name) in a publish folder | Library DWGs in an 867 folder plus a cleaned copy of the master |
| Changes to existing files | None, proven by fingerprints of every file read | None; the cleaned master is swapped in only after review |
| How often | Every time the master changes (re-snapshot) | Once per equipment file, at setup |
| Status | Built; needs testing | To build after Tool 1 is proven |

Table 1. Two tools, two jobs

# 3. Ground Rules (Non-Negotiable)

- Nothing that is read is ever changed. Every file the tools read, master and references alike, is fingerprinted (SHA-256) before and after, and the report shows the result.

- Every result is a new file. Nothing is edited in place; the cleaned master replaces the original only after your review.

- First runs happen in a local sandbox (C:\DWG Sandbox) on copied files, never on P: and never inside a Plant 3D project folder.

- Other projects' files are only ever read. Writing copies of their blocks into 867 (Tool 2) is a decision for you and their project leads.

# 4. Course of Action

| Step | Action | Who | Target | Exit gate |
| --- | --- | --- | --- | --- |
| 1 | Run setup.bat and run.bat; run the built-in self-test (background engine) | John | Day 1 AM | All synthetic cases PASS |
| 2 | Extend Tool 1 to fingerprint every referenced file; add the dependency inventory and sandbox copier | Claude | Day 1, in parallel | Code delivered and reviewed |
| 3 | Dry-run inventory of the 867 master: every dependency, grouped by owning project (nothing copied) | John + tool | Day 1 PM | Full picture of what the master borrows |
| 4 | Copy the master and its dependencies into the sandbox; confirm nothing points outside it | John + tool | Day 2 AM | Sandbox sealed; originals unchanged |
| 5 | Tool 1: snapshot the sandbox master; overlay compare against the source | John + Claude | Day 2 | Validation passes; no visible differences |
| 6 | Fix round for anything the first real run exposes | Claude | Day 2 to 3 | Re-run passes |
| 7 | Downstream proof: point one piping or electrical drawing (copy) at the snapshot; measure | John | Day 3 | Open, regen and pan times recorded before vs after |
| 8 | Go live with Tool 1: snapshot the real master to the publish folder; move 2D sets over one at a time | John | End of week 1 | Sets on the snapshot; old paths logged for rollback |
| 9 | Build Tool 2: dry-run report, then bring in, explode, wblock to the 867 library, cleaned master copy | Claude | Week 2 | Code delivered and reviewed |
| 10 | Run Tool 2 in the sandbox, review with the designer, then on the real master; swap in after sign-off | John + designer | End of week 2 | Zero outside dependencies; designer signs off |

Table 2. Expedited sequence with exit gates

# 5. After Go-Live: Re-Snapshots

The snapshot keeps one fixed file name so downstream references never break. Any change to the master after the cut-off is published by re-snapshotting. A later addition dates each snapshot inside the file: a revision chart on a non-plotting layer, a required change description, and a dated copy of the previous snapshot kept for audit. The app will also flag when the master has changed since the last snapshot. Whether to make the master read-only with a required change note on every save is deferred until early-stage changes slow down.

# 6. Decisions Needed

| Decision | Why it matters | Owner |
| --- | --- | --- |
| Are the borrowed items Xrefs, inserted blocks, or both? | Determines exactly what Tool 2 has to pull in | John + designer |
| 867 library folder location and naming | Cleaned blocks live there permanently | John |
| Copying other projects' content into 867 | Ownership and revision control across projects | John + other project leads |
| Snapshot publish folder and file name | Piping and electrical sets will reference it long term | John |
| Who may run a re-snapshot after go-live | Keeps downstream references controlled | John |

Table 3. Decisions that unblock the schedule

# 7. How Progress Is Measured

Safety: zero changes to any file read, shown by fingerprints in every report. Benefit: 2D drawing open and regen time and file size, before vs after the snapshot. Project health: outside-project dependencies in the 867 master, driven to zero by Tool 2. Throughput: 2D drawings moved onto the snapshot.